## Cover
AI Factory Project Plan
TriZetto Managed Cloud Services — LLMWiki as Shared Knowledge Fabric
Generated: May 15, 2026 ¦ v2.1 — Skills + Hard Harness ¦ AWS Account: 392568849512 ¦ Region: us-east-1
Purpose
This workbook tracks the end-to-end delivery of the AI Factory initiative: deploying LLMWiki as a
shared knowledge fabric for 10 AI agent use cases across the TriZetto Managed Cloud Services lifecycle.
It covers gap analysis, security & governance standards, phased project plan, and UC1 POC checklist.
Workbook Tabs
Cover | This page — project overview and legend
Project Plan | Gantt-style task plan across Phase 0–4
Gap Analysis — LLMWiki | ~35 identified gaps with remediation owners and phases
AI Security Standards | ~30 security requirements mapped to AWS/Bedrock controls
AI Governance Standards | ~30 governance policies enforced via LLMWiki
POC Checklist — UC1 S2S | ~25 validation checks for the Sales-to-Service POC
Colour Legend
Phase Header Row
POC / Discovery Task
Security / Governance Task
Production Task
High Impact / Gap
Medium Impact / Planned
Low Impact / Implemented
Key Stakeholders & Approved Tools
Approved AI Tools: Microsoft 365 Copilot, Claude (Anthropic), GitHub Copilot, Windsurf IDE, Arize AI
Approved AWS: Amazon Bedrock (Claude models only), Amazon Kendra, SageMaker, Amazon Q Business, Amazon Q Developer
Approved Other: Microsoft Fabric, ServiceNow
NOT Approved: AWS Strands, Kiro Autonomous Agent, AWS DevOps Guru, non-Claude Bedrock models

## Project Plan
Phase | Task ID | Task Name | Owner | Duration (days) | Start Week | End Week | Dependencies | Status | Notes
PHASE 0 |  | LLMWiki Core Loop POC — Deploy Existing Code (2 weeks)
Phase 0 | P0-T01 | Provision S3 bucket & enable SSE-S3 encryption | DevOps | 1 | W1 | W1 | — | Complete | Bucket: llmwiki-kb-prod, region us-east-1
Phase 0 | P0-T02 | Upload seed markdown files to S3 | DevOps | 1 | W1 | W1 | P0-T01 | Complete | ~20 runbook/playbook pages from Confluence export
Phase 0 | P0-T03 | Create Bedrock Knowledge Base (S3 Vectors data source) | ML Eng | 2 | W1 | W1 | P0-T01 | Complete | Model: amazon.titan-embed-text-v2:0; chunking 1000 tokens
Phase 0 | P0-T04 | Deploy DynamoDB tables (wiki_pages, contributions, audit_log) | DevOps | 1 | W1 | W1 | — | Complete | PAY_PER_REQUEST billing; enable PITR
Phase 0 | P0-T05 | Deploy Lambda functions (ingest, retrieve, contribute) | ML Eng | 2 | W1 | W1 | P0-T03,P0-T04 | Complete | Python 3.12; ARM64; 512 MB memory
Phase 0 | P0-T06 | Wire API Gateway REST API → Lambda | DevOps | 1 | W1 | W1 | P0-T05 | Complete | Stages: dev, prod; enable CloudWatch logging
Phase 0 | P0-T07 | Deploy Streamlit UI (EC2 t3.small or Fargate) | DevOps | 2 | W2 | W2 | P0-T06 | Complete | Basic wiki browse + contribute form
Phase 0 | P0-T08 | Smoke test: ingest→retrieve→respond loop | ML Eng | 1 | W2 | W2 | P0-T07 | Complete | 10 test queries against seed content
Phase 0 | P0-T09 | Enable CloudTrail for all API calls | SecOps | 1 | W2 | W2 | P0-T06 | Complete | S3 trail bucket: llmwiki-audit-logs
Phase 0 | P0-T10 | POC sign-off & demo to stakeholders | PM | 1 | W2 | W2 | P0-T08 | Complete | 15-min demo; record loom
PHASE 1 |  | Business Demo — SharePoint Connector, PDF Support, Streamlit UI (3 weeks)
Phase 1 | P1-T01 | Implement SharePoint Online connector (Graph API) | ML Eng | 3 | W3 | W3 | P0-T05 | Complete | OAuth2 app registration in Entra ID
Phase 1 | P1-T02 | PDF ingestion pipeline (Textract → markdown → S3) | ML Eng | 3 | W3 | W3 | P0-T05 | Complete | AWS Textract for scanned PDFs
Phase 1 | P1-T03 | Enhance Streamlit UI: search, tag filter, contribution form | FE Dev | 3 | W3 | W3 | P0-T07 | Complete | human_review_required flag visible
Phase 1 | P1-T04 | Implement /wiki/ingest API endpoint | BE Dev | 2 | W4 | W4 | P1-T01,P1-T02 | Complete | POST body: {source_type, url, metadata}
Phase 1 | P1-T05 | Implement /wiki/ask API endpoint (v0 — no domain routing) | BE Dev | 3 | W4 | W4 | P0-T05 | Complete | Returns {answer, sources[], confidence}
Phase 1 | P1-T06 | Implement /wiki/contribute endpoint | BE Dev | 2 | W4 | W4 | P0-T04 | Complete | Writes to pending/ staging; sets human_review_required
Phase 1 | P1-T07 | Demo to business stakeholders | PM | 1 | W5 | W5 | P1-T03,P1-T05 | Complete | Focus: SharePoint round-trip + agent-contributed page
Phase 1 | P1-T08 | Collect feedback & update backlog | PM | 2 | W5 | W5 | P1-T07 | Complete | GitHub Issues; prioritize by UC
PHASE 2 |  | TAG→AgentCore POC — UC1 Sales-to-Service Agent Queries LLMWiki (3 weeks)
Phase 2 | P2-T01 | Register MCP tool wiki_ask in AgentCore | ML Eng | 2 | W6 | W6 | P1-T05 | Complete | wiki_ask MCP tool registered; SK-02 WikiQuerySkill deployed
Phase 2 | P2-T02 | Register MCP tool wiki_contribute in AgentCore | ML Eng | 1 | W6 | W6 | P1-T06 | Complete | wiki_contribute MCP tool registered; SK-03 WikiContributeSkill deployed
Phase 2 | P2-T03 | Configure AgentCore Gateway (IAM, SigV4, agent identity) | DevOps | 2 | W6 | W6 | — | Complete | IAM role llmwiki-agentcore-s2s-role deployed; SigV4 verified
Phase 2 | P2-T04 | Deploy UC1 Sales-to-Service agent in AgentCore | ML Eng | 3 | W7 | W7 | P2-T01,P2-T03 | Complete | UC1 Orchestrator Lambda deployed: llmwiki-uc1-orchestrator; Claude Sonnet 4.6
Phase 2 | P2-T05 | Build Cedar policy prototype (Zero-Inference Policy) | ML Eng | 3 | W7 | W7 | P2-T04 | In Progress | Cedar policy prototype designed; implementing in Phase 4
Phase 2 | P2-T06 | Validate TAG persona manifest migration → AgentCore config | ML Eng | 2 | W7 | W7 | P2-T04 | Complete | TAG→AgentCore persona migration documented in LLMWikiDesign.md §20
Phase 2 | P2-T07 | Wrap legacy Azure AI Search as Lambda (RAG bridge) | ML Eng | 2 | W7 | W7 | — | Deferred | Azure AI Search bridge not required; Bedrock KB S3 Vectors covers retrieval
Phase 2 | P2-T08 | End-to-end test: SOW upload → wiki page → agent query → response | QA | 2 | W8 | W8 | P2-T04,P2-T07 | Complete | E2E test: 20 UC1 queries via UC1 Orchestrator; all 5 skills verified
Phase 2 | P2-T09 | UC1 POC sign-off & stakeholder review | PM | 1 | W8 | W8 | P2-T08 | Complete | UC1 POC demo delivered; skill + harness architecture validated
PHASE 2 — SKILLS |  | Reusable Skill Architecture — UC1 POC (SK-01 to SK-05)
Phase 2 | SK-T01 | Deploy SK-01 ContextBootstrapSkill Lambda | ML Eng | 1 | W6 | W6 | P2-T04 | Complete | llmwiki-skill-context-bootstrap deployed; loads customer wiki pages + UC1 playbook
Phase 2 | SK-T02 | Deploy SK-02 WikiQuerySkill Lambda | ML Eng | 1 | W6 | W6 | P2-T01 | Complete | llmwiki-skill-wiki-query deployed; confidence: high/medium/low; action_items[]
Phase 2 | SK-T03 | Deploy SK-03 WikiContributeSkill Lambda | ML Eng | 1 | W6 | W6 | P2-T02 | Complete | llmwiki-skill-wiki-contribute deployed; human_review_required gate; contributing_agent frontmatter
Phase 2 | SK-T04 | Deploy SK-04 ArtifactResolutionSkill Lambda | ML Eng | 1 | W7 | W7 | SK-T01 | Complete | llmwiki-skill-artifact-resolution deployed; persona-template auto-fill; completion_pct metric
Phase 2 | SK-T05 | Deploy SK-05 GapDetectionSkill Lambda | ML Eng | 1 | W7 | W7 | SK-T02 | Complete | llmwiki-skill-gap-detection deployed; blocking gap detection; human_prompt per gap
Phase 2 | SK-T06 | Deploy UC1 Orchestrator Lambda (SK-01 through SK-05) | ML Eng | 2 | W7 | W7 | SK-T01,SK-T05 | Complete | llmwiki-uc1-orchestrator deployed; invokes all 5 skills in sequence; E2E tested
Phase 2 | SK-T07 | Build Skills Hub Streamlit page | FE Dev | 1 | W8 | W8 | SK-T06 | Complete | /skills_hub — shows all 5 skill cards with live invocation + latency badges
Phase 2 | SK-T08 | Build Skill Builder Streamlit page | FE Dev | 1 | W8 | W8 | SK-T06 | Complete | /skill_builder — test each skill in isolation with custom inputs
Phase 2 | SK-T09 | Build UC1 Agent Demo Streamlit page (step-by-step) | FE Dev | 2 | W8 | W8 | SK-T06 | Complete | /agent_demo — 6-step walkthrough; SK-01…SK-05 executed sequentially with skill badges
Phase 2 | SK-T10 | E2E skill smoke test (test_skills_e2e.sh) | QA | 1 | W8 | W8 | SK-T06 | Complete | All 5 skill Lambdas + orchestrator verified; ARNs confirmed in account 392568849512
PHASE 2 — HARNESS |  | Hard Harness — UC1 8-Phase State Machine
Phase 2 | HRN-T01 | Deploy DynamoDB harness_runs table | DevOps | 0.5 | W9 | W9 | — | Complete | llmwiki-harness-runs; PAY_PER_REQUEST; 2 GSIs (status_index, engagement_status_index); TTL 30d
Phase 2 | HRN-T02 | Deploy DynamoDB workspace_files table | DevOps | 0.5 | W9 | W9 | — | Complete | llmwiki-workspace-files; PAY_PER_REQUEST; phase_index GSI; TTL 30d
Phase 2 | HRN-T03 | Deploy llmwiki-gatekeeper Lambda | ML Eng | 1 | W9 | W9 | HRN-T01 | Complete | 30s/256MB; validates prereqs; generates Claude greeting; returns 8-phase manifest; Bedrock-generated questions
Phase 2 | HRN-T04 | Deploy llmwiki-uc1-harness Lambda (8-phase driver) | ML Eng | 3 | W9 | W10 | HRN-T01,HRN-T02,SK-T06 | Complete | 900s/1024MB; 8-phase state machine; pause/resume at Phase 3; get_status polling action; full DynamoDB audit trail
Phase 2 | HRN-T05 | Implement async polling (get_status + InvocationType=Event) | ML Eng | 1 | W10 | W10 | HRN-T04 | Complete | Fires Lambda async; UI polls DynamoDB every 3s; phase tiles animate live; no blocking spinner
Phase 2 | HRN-T06 | Update IAM: Streamlit can invoke harness Lambdas + read harness tables | DevOps | 0.5 | W10 | W10 | HRN-T03,HRN-T04 | Complete | llmwiki-streamlit-skills-invoke policy updated; HarnessStateRead + HarnessReportDownload added
Phase 2 | HRN-T07 | Build harness_demo.py Streamlit page | FE Dev | 2 | W10 | W10 | HRN-T03,HRN-T04 | Complete | /harness_demo; two-column layout (chat 60% + locked plan 40%); Phase 3 hint panel; async polling; download button
Phase 2 | HRN-T08 | E2E harness smoke test: gatekeeper → pause → resume → 8 phases | QA | 1 | W10 | W10 | HRN-T07 | Complete | CUST001 run: phases 1-2 complete in 10s; paused at 3; resumed; all 8 complete in 30s; S3 report generated
Phase 2 | HRN-T09 | Update LLMWikiDesign.md §22 + LLMWikiDesignMVP.md with harness details | Arch | 1 | W10 | W10 | HRN-T08 | Complete | Sections 22.12–22.15 added: deployed resources, async polling arch, latency budget, error contract
Phase 2 | HRN-T10 | Update AIFactoryProjectPlan.xlsx with skills + harness impact | PM | 1 | W10 | W10 | HRN-T09 | Complete | All 6 sheets updated: Project Plan, Gap Analysis, Security, Governance, POC Checklist
PHASE 3 |  | Business Knowledge API — All 10 UC Agents (6 weeks)
Phase 3 | P3-T01 | Design domain routing logic (/wiki/ask?domain=UC1..UC10) | Arch | 3 | W9 | W9 | P1-T05 | Not Started | Route by metadata tag; fallback to global
Phase 3 | P3-T02 | Implement UC1–UC5 agent system prompts & tool wiring | ML Eng | 5 | W9 | W10 | P2-T04 | Not Started | UC1 S2S, UC2 Env Prov, UC3 IAM, UC4 Biz Config, UC5 Data Mig
Phase 3 | P3-T03 | Implement UC6–UC10 agent system prompts & tool wiring | ML Eng | 5 | W10 | W11 | P3-T02 | Not Started | UC6 SIT, UC7 E2E Test, UC8 Cutover, UC9 PTO/Handover, UC10 Hypercare
Phase 3 | P3-T04 | Ingest seed content for all 10 use case domains | Content | 5 | W9 | W10 | P1-T04 | Not Started | Runbooks, playbooks, IaC templates, SOW templates
Phase 3 | P3-T05 | Implement structured response contract (Binary Answer) | BE Dev | 2 | W10 | W10 | P3-T01 | Not Started | Fields: answer (yes/no/unknown), evidence[], confidence
Phase 3 | P3-T06 | Add Bedrock Guardrails to all agent endpoints | SecOps | 3 | W10 | W11 | P3-T02 | Not Started | Replaces Azure AI Content Safety; prompt injection filter
Phase 3 | P3-T07 | Implement contributing_agent frontmatter in wiki pages | BE Dev | 2 | W11 | W11 | P3-T04 | Not Started | Fields: agent_id, contributing_at, human_reviewed
Phase 3 | P3-T08 | HIPAA BAA confirmation per component (Bedrock, DynamoDB, S3) | SecOps | 3 | W11 | W12 | — | Not Started | Document covered services; flag any gaps
Phase 3 | P3-T09 | Real-time hallucination detection integration (Arize AI) | ML Eng | 4 | W12 | W12 | P3-T02 | Not Started | Arize Phoenix traces via OpenTelemetry; alert on low confidence
Phase 3 | P3-T10 | Build human review queue in Streamlit (pending/ area) | FE Dev | 3 | W12 | W13 | P1-T03 | Not Started | SME approval workflow; DynamoDB status update
Phase 3 | P3-T11 | Vector alignment reporting (V1/V2/V3 tags per AI Handbook) | ML Eng | 2 | W13 | W13 | P3-T04 | Not Started | Quarterly dashboard in Streamlit
Phase 3 | P3-T12 | Integration test: all 10 agents × LLMWiki API | QA | 5 | W13 | W14 | P3-T03 | Not Started | 50 test queries per UC; recall/precision metrics
Phase 3 | P3-T13 | Performance baseline & cost report | DevOps | 2 | W14 | W14 | P3-T12 | Not Started | Target: p95 latency < 3s; cost per query < $0.01
PHASE 4 |  | Production — Security, CI/CD, OpenSearch, Cognito Auth (8 weeks)
Phase 4 | P4-T01 | Migrate vector store from S3 Vectors → OpenSearch Serverless | ML Eng | 5 | W15 | W16 | P3-T12 | Not Started | If S3 Vectors cost/scale limits hit; evaluate in P3
Phase 4 | P4-T02 | Implement Cognito User Pool + OIDC federation (Entra ID) | SecOps | 4 | W15 | W16 | — | Not Started | Groups: wiki-admin, wiki-contributor, agent-readonly
Phase 4 | P4-T03 | Add WAF to API Gateway (OWASP rules + rate limiting) | SecOps | 3 | W15 | W15 | P0-T06 | Not Started | Block >100 req/min per IP; SQL-injection rules
Phase 4 | P4-T04 | Enforce TLS 1.2+ on all endpoints; VPC endpoints for S3/DynamoDB | SecOps | 2 | W16 | W16 | P4-T02 | Not Started | VPC endpoint policy: deny public access
Phase 4 | P4-T05 | API key rotation pipeline (Secrets Manager + Lambda) | SecOps | 2 | W16 | W16 | P4-T02 | Not Started | 30-day rotation; auto-notify agents
Phase 4 | P4-T06 | CI/CD pipeline: GitHub Actions → ECR → Lambda/ECS deploy | DevOps | 5 | W17 | W18 | — | Not Started | PR lint + unit test gate; Checkov IaC scan
Phase 4 | P4-T07 | Infrastructure as Code: CDK stacks for all resources | DevOps | 5 | W17 | W18 | P4-T06 | Not Started | Separate stacks: storage, api, agents, monitoring
Phase 4 | P4-T08 | DynamoDB audit log for all agent contributions | BE Dev | 3 | W18 | W19 | P3-T07 | Not Started | Table: wiki_audit; TTL 7 years for HIPAA
Phase 4 | P4-T09 | CloudTrail + Config rules for compliance | SecOps | 2 | W18 | W18 | P0-T09 | Not Started | Config rule: s3-bucket-server-side-encryption-enabled
Phase 4 | P4-T10 | Load testing & chaos engineering | QA | 4 | W19 | W20 | P4-T06 | Not Started | Locust: 1000 concurrent queries; inject S3 fault
Phase 4 | P4-T11 | Security penetration test (external) | SecOps | 5 | W19 | W20 | P4-T03,P4-T04 | Not Started | Scope: API Gateway, Bedrock endpoint, Streamlit UI
Phase 4 | P4-T12 | ServiceNow integration: auto-create change records for wiki updates | BE Dev | 3 | W20 | W21 | P4-T08 | Not Started | Webhook → ServiceNow Change Management
Phase 4 | P4-T13 | Final UAT with all 10 agent teams | QA | 5 | W21 | W22 | P4-T10 | Not Started | Sign-off criteria in POC Checklist tab
Phase 4 | P4-T14 | Production go-live & hypercare monitoring | DevOps | 5 | W22 | W22 | P4-T13 | Not Started | PagerDuty alerts; 2-week hypercare period

## Gap Analysis — LLMWiki
Gap ID | Gap Category | Gap Description | Current State | Required State | Impact (H/M/L) | Effort (H/M/L) | Remediation Action | Phase to Close | Approved Tool to Close | Status
1. LLMWiki Infrastructure Gaps
G-001 | LLMWiki Infrastructure | LLMWiki Phase 1 code not deployed to AWS | Code complete; no cloud resources | Running in AWS account 392568849512 | H | M | Execute Phase 0 deployment runbook; provision S3, DynamoDB, Lambda, API GW | P0 | Amazon Bedrock, AWS CDK | Closed
G-002 | LLMWiki Infrastructure | No authentication on LLMWiki API endpoints | Unauthenticated API Gateway | SigV4 or Cognito JWT on all endpoints | H | M | Add Cognito User Pool; enforce Authorization header in API GW | P4 | Amazon Cognito (Bedrock) | Open
G-003 | LLMWiki Infrastructure | No CI/CD pipeline for LLMWiki code | Manual deploy; no IaC | GitHub Actions → CDK deploy pipeline | M | M | Build GitHub Actions workflow; add Checkov IaC scan gate | P4 | GitHub Copilot, AWS CDK | Open
G-004 | LLMWiki Infrastructure | No VPC deployment; resources on public internet | Public Lambda + API GW | VPC-bound resources; VPC endpoints for S3/DynamoDB | H | H | Deploy Lambda in VPC; create S3 and DynamoDB VPC endpoints | P4 | AWS CDK | Open
G-005 | LLMWiki Infrastructure | No automated Bedrock KB sync schedule | Manual sync only | Scheduled sync every 24h (EventBridge rule) | M | L | Add EventBridge cron → Lambda KB sync trigger | P1 | Amazon Bedrock, AWS Lambda | Closed
2. Business Knowledge API Gaps
G-006 | Business Knowledge API | No /wiki/ask endpoint (query API) | No structured query surface | POST /wiki/ask returns {answer, sources[], confidence} | H | M | Implement wiki_retrieve Lambda + API GW route; wire to Bedrock KB | P1 | Amazon Bedrock | Closed
G-007 | Business Knowledge API | No domain routing by use-case | Single flat knowledge base | Route by domain=UC1..UC10 metadata filter | M | M | Add query filter param; tag all documents with use_case metadata | P3 | Amazon Bedrock | In Progress
G-008 | Business Knowledge API | No structured JSON response contract | Free-text LLM answer | Structured: {answer(yes/no/unknown), evidence[], confidence, sources[]} | H | M | Enforce Binary Answer Contract in system prompt + Lambda response schema | P2 | Claude (Anthropic), Amazon Bedrock | In Progress
G-009 | Business Knowledge API | No /wiki/ingest endpoint | Manual S3 upload only | POST /wiki/ingest accepts SharePoint URL or PDF upload | M | M | Implement ingest Lambda: Graph API → Textract → S3 → KB sync | P1 | Amazon Bedrock, AWS Textract | Closed
G-010 | Business Knowledge API | No /wiki/contribute endpoint for agent-authored pages | No agentic contribution surface | POST /wiki/contribute creates pending/ wiki page with frontmatter | H | M | Implement contribute Lambda; write to DynamoDB pending table; set human_review_required | P1 | Amazon Bedrock, Claude (Anthropic) | Closed
3. AgentCore Integration Gaps
G-011 | AgentCore Integration | No MCP tool wiki_ask registered in AgentCore | No tool definition | MCP tool registered with full input/output schema | H | M | Define tool spec; POST to AgentCore Gateway; unit test via CLI | P2 | Amazon Bedrock (AgentCore) | Closed
G-012 | AgentCore Integration | No MCP tool wiki_contribute in AgentCore | No contribution path for agents | MCP tool wiki_contribute registered; agents can author pages | H | M | Define tool spec; wire to /wiki/contribute Lambda | P2 | Amazon Bedrock (AgentCore) | Closed
G-013 | AgentCore Integration | No agent identity tracking for wiki contributions | Anonymous contributions | Each contribution tagged with agent_id, contributing_at, model_version | H | M | Pass AgentCore identity headers to Lambda; store in DynamoDB | P2 | Amazon Bedrock (AgentCore) | Closed
G-014 | AgentCore Integration | No agent contribution audit trail | No audit log | DynamoDB wiki_audit table; every contribution recorded | H | M | Implement audit Lambda interceptor; write to wiki_audit on every write | P3 | Amazon DynamoDB | Open
G-015 | AgentCore Integration | Human review pipeline not integrated with AgentCore feedback loop | Manual review in Streamlit only | Approved pages auto-promote from pending/ to published/; agent notified | M | M | Add approval webhook; update DynamoDB status; trigger KB re-sync | P3 | Amazon Bedrock, Amazon DynamoDB | In Progress
4. TAG→AgentCore Migration Gaps
G-016 | TAG→AgentCore Migration | Persona manifest / config management has no direct AgentCore analog | TAG: YAML persona manifests | AgentCore: equivalent config object with persona, tools, constraints | H | H | Build custom persona config object; map TAG fields to AgentCore session params | P2 | Amazon Bedrock (AgentCore), Claude (Anthropic) | Open
G-017 | TAG→AgentCore Migration | No-fallback routing not supported natively in AgentCore | TAG: explicit no-fallback rule | AgentCore: requires custom routing logic | H | H | Implement custom routing Lambda; deny requests with no confident KB match | P2 | Amazon Bedrock (AgentCore) | Open
G-018 | TAG→AgentCore Migration | Azure AI Search (RAG) must be wrapped as custom Lambda | Azure AI Search endpoint | Lambda bridge to existing Azure AI Search until migrated | H | H | Build AzureSearchBridgeLambda; invoke from AgentCore tool; plan migration timeline | P2 | AWS Lambda, Amazon Bedrock | Open
G-019 | TAG→AgentCore Migration | Zero-Inference Policy not native in AgentCore | TAG: custom policy engine | Cedar policy prototype to deny low-confidence answers | H | H | Prototype Cedar policy; integrate as Lambda authorizer on /wiki/ask | P2 | Amazon Bedrock (AgentCore) | Open
G-020 | TAG→AgentCore Migration | Binary Answer Contract not enforced in AgentCore | Free-form agent responses | Structured yes/no/unknown response with evidence required | H | M | Enforce in system prompt + Lambda response validator; reject malformed responses | P2 | Claude (Anthropic) | In Progress
G-021 | TAG→AgentCore Migration | HIPAA BAA coverage not confirmed for all AgentCore components | Unknown BAA status per component | All components with PHI/PII must be under BAA | H | M | Audit: Bedrock, S3, DynamoDB, API GW, Lambda, CloudWatch all under Cognizant AWS BAA | P3 | Amazon Bedrock | Open
G-022 | TAG→AgentCore Migration | Real-time hallucination detection not available in AgentCore natively | No hallucination monitoring | Real-time trace + alert when confidence < threshold | H | H | Integrate Arize AI Phoenix via OpenTelemetry; add alert Lambda | P3 | Arize AI | Open
G-023 | TAG→AgentCore Migration | Azure AI Content Safety → Bedrock Guardrails migration | Azure AI Content Safety active | Bedrock Guardrails replaces Azure safety filters | M | M | Configure Bedrock Guardrails: prompt injection, PII detection, topic denial | P2 | Amazon Bedrock (Guardrails) | In Progress
G-024 | TAG→AgentCore Migration | Multi-agent Strands framework used in TAG (not approved) | SK/Strands-based orchestration | Must migrate to AgentCore-native or approved framework | H | H | Map Strands agents to AgentCore agents; validate A2A protocol for Neuro AI roadmap | P3 | Amazon Bedrock (AgentCore) | Open
G-025 | TAG→AgentCore Migration | Self-hosted/on-premise deployment not supported in AgentCore | TAG supports on-premise | Cloud-only deployment accepted by stakeholders | L | L | Document as architectural constraint; no remediation required | P0 | — | Acknowledged
5. Security Gaps
G-026 | Security | No WAF on API Gateway endpoints | Unprotected public API | WAF with OWASP rules + rate limiting (100 req/min/IP) | H | M | Add AWS WAF WebACL to API GW stage; configure managed rule groups | P4 | Amazon Bedrock (API GW) | Open
G-027 | Security | TLS version not enforced on API endpoints | Default TLS (may allow TLS 1.0/1.1) | TLS 1.2+ enforced on all endpoints | H | L | Set SecurityPolicy: TLS_1_2 on API GW custom domain; verify Lambda function URLs | P4 | AWS CDK | Open
G-028 | Security | No data encryption in transit verified for S3↔Lambda path | Assumed HTTPS but not validated | All S3 calls use HTTPS; bucket policy denies HTTP | M | L | Add S3 bucket policy: deny http requests; validate in Config rule | P4 | Amazon S3 | Open
G-029 | Security | No API key rotation process | Static API keys if used | 30-day rotation via Secrets Manager + Lambda | M | M | Implement rotation Lambda; update API GW usage plan; notify consumers | P4 | AWS Secrets Manager | Open
G-030 | Security | No prompt injection prevention beyond system prompt | Basic system prompt only | Bedrock Guardrails input filter + validation Lambda | H | M | Enable Bedrock Guardrails prompt injection filter; add input sanitization in Lambda | P3 | Amazon Bedrock (Guardrails) | Open
6. Governance Gaps
G-031 | Governance | No AI lineage tracking (doc → wiki page → agent answer → citation) | No lineage metadata | Full lineage: source_doc_id → wiki_page_id → query_id → answer_id | H | H | Add lineage metadata to each DynamoDB record; surface in Streamlit UI | P3 | Amazon DynamoDB, Arize AI | Open
G-032 | Governance | No vector alignment tagging (V1/V2/V3 per AI Handbook) | Untagged vectors | All wiki pages tagged with alignment_tier: V1/V2/V3 | M | M | Add alignment_tier to frontmatter schema; report quarterly | P3 | Amazon Bedrock | Open
G-033 | Governance | No agent contribution audit report | No governance reporting | Monthly report: contributions per agent, review rate, approval time | M | M | Build Athena query over DynamoDB export; Streamlit dashboard tab | P3 | Microsoft Fabric, Amazon Athena | Open
7. Knowledge Content Gaps
G-034 | Knowledge Content | No seed content ingested for any use case domain | Empty knowledge base | ≥20 pages per UC (200 total) seeded before Phase 3 agent rollout | H | H | Assign content owners per UC; extract from Confluence/SharePoint; ingest via P1-T04 | P3 | Microsoft 365 Copilot, Amazon Bedrock | Open
G-035 | Knowledge Content | No customer-specific wiki pages (post-onboarding) | Generic runbooks only | Customer wiki pages created during UC2 Env Provisioning | M | M | UC2 agent contributes customer page on env creation; SME reviews | P3 | Claude (Anthropic), Amazon Bedrock | Open
8. Skill Architecture Gaps
G-036 | Skill Architecture | Shared IAM role across all skill + harness Lambdas | llmwiki-skills-lambda-role shared by 7 Lambdas | Dedicated per-function IAM roles with minimum permissions | M | M | Create separate role per Lambda function; use Terraform for_each | P4 | AWS IAM, AWS CDK | Open
G-037 | Skill Architecture | Bedrock:InvokeModel wildcard (*) in skill Lambda role | IAM allows any Bedrock model invocation | Scope to approved Claude model ARNs only | M | L | Replace Resource="*" with specific model ARNs in iam_skills.tf | P4 | AWS IAM | Open
G-038 | Skill Architecture | SNS:Publish wildcard (*) in skill Lambda role | IAM allows SNS publish to any topic | Scope to specific SNS topic ARNs | L | L | Replace Resource="*" with specific topic ARNs in iam_skills.tf | P4 | AWS IAM | Open
G-039 | Skill Architecture | No Bedrock model invocation logging to S3 | Model inputs/outputs logged to CloudWatch only | Bedrock model invocation logging to S3 for SOC2/audit compliance | H | L | Enable model invocation logging in Bedrock console; S3 bucket + retention policy | P3 | Amazon Bedrock | Open
G-040 | Skill Architecture | Phase 6 gap detection sub-agents run sequentially (not parallel) | SK-05 invoked 3x in a loop (~30s) | Parallel sub-agent invocation via asyncio.gather or Step Functions Map | M | M | Refactor _phase6_gap_detection to use asyncio.gather for concurrent SK-05 calls | P3 | AWS Lambda, Amazon Bedrock | Open
9. Hard Harness Gaps
G-041 | Hard Harness | No authentication on Streamlit harness_demo page | ALB serves UI without any auth (POC/internal only) | Cognito or corporate SSO (OIDC) before any real customer data | H | M | Add Cognito User Pool authorizer on ALB listener; map Entra ID groups to roles | P4 | Amazon Cognito | Open
G-042 | Hard Harness | DOCX output is plain-text .txt (POC placeholder) | S3 report is plain text; not a real Word document | python-docx Lambda layer producing formatted .docx deliverable | M | M | Build Lambda container image with python-docx; replace _build_report_text() with docx generation | P3 | AWS Lambda (container image) | Open
G-043 | Hard Harness | Presigned URL expires in 1 hour (too short for business handoff) | report_download_url TTL = 3600s | Extend to 24-48h or replace with CloudFront signed URL | M | L | Increase presigned URL TTL to 86400s or add CloudFront key pair for signed URLs | P3 | Amazon S3, Amazon CloudFront | Open
G-044 | Hard Harness | PHI/PII detection not implemented on wiki contributions | SK-03 writes any content to wiki without PHI scan | Bedrock Guardrails on SK-03 path to detect and block PHI before wiki write | H | M | Enable Bedrock Guardrails with PII filter on WikiContributeSkill Lambda | P3 | Amazon Bedrock (Guardrails) | Open
G-045 | Hard Harness | No multi-user isolation in harness (latest run wins per engagement_id) | engagement_id used as partition key; concurrent users overwrite each other | Add agent_session_id as secondary partition; isolate per-user runs | M | M | Add session_id to harness DynamoDB key; pass from Streamlit session state | P3 | Amazon DynamoDB | Open

## AI Security Standards
Standard ID | Category | Standard Name | Requirement | Implementation in LLMWiki/AgentCore | Approved Tool | Compliance Gate | Status
Data Protection
SEC-D-001 | Data Protection | S3 Encryption at Rest | All S3 buckets must use SSE-S3 or SSE-KMS | SSE-S3 enabled on llmwiki-278e7e22; bucket Block Public Access enabled | Amazon S3 | Phase 0 | Active
SEC-D-002 | Data Protection | DynamoDB Encryption at Rest | DynamoDB tables encrypted with AWS-managed KMS key | DynamoDB SSE enabled on all 7 tables including harness_runs + workspace_files | Amazon DynamoDB | Phase 0 | Active
SEC-D-003 | Data Protection | TLS 1.2+ in Transit | All API endpoints enforce TLS 1.2 minimum | API GW SecurityPolicy: TLS_1_2; deny HTTP via bucket policy | Amazon API Gateway | Phase 4 | Gap
SEC-D-004 | Data Protection | PII/PHI Handling in Wiki Pages | PHI fields in wiki pages must be tagged and access-controlled | Mark PHI fields in frontmatter; restrict via IAM condition on DynamoDB | Amazon DynamoDB, Amazon Bedrock | Phase 3 | Planned
SEC-D-005 | Data Protection | Data Residency | All data must remain in us-east-1 | All resources in us-east-1; S3 Block Public Access enabled; no cross-region | AWS Organizations SCP | Phase 0 | Active
Identity & Access
SEC-I-001 | Identity & Access | IAM Least Privilege | Lambda execution roles must have minimal permissions | Per-function roles for Streamlit + pipeline; skill Lambdas share llmwiki-skills-lambda-role — split in P4 | AWS IAM | Phase 0 | Partial
SEC-I-002 | Identity & Access | SigV4 for Agent Auth | AgentCore agents must authenticate via SigV4 | AgentCore S2S role (llmwiki-agentcore-s2s-role) deployed; SigV4 enforced on Business API | Amazon Bedrock (AgentCore) | Phase 2 | Active
SEC-I-003 | Identity & Access | OIDC Federation (Entra ID) | Human users authenticate via Cognizant Entra ID SSO | Cognito User Pool with OIDC IdP: Entra ID tenant; map groups to roles | Amazon Cognito | Phase 4 | Gap
SEC-I-004 | Identity & Access | Agent Identity Tracking | Every API call must carry agent_id for attribution | agent_id passed in skill invocation payload; stored in wiki-log DynamoDB table | Amazon Bedrock (AgentCore) | Phase 2 | Active
SEC-I-005 | Identity & Access | No Shared Credentials | No hardcoded credentials in Lambda code or config | No hardcoded credentials; SSM for ARN discovery; Secrets Manager for third-party keys | AWS Secrets Manager, GitHub Copilot | Phase 0 | Active
API Security
SEC-A-001 | API Security | WAF on API Gateway | AWS WAF WebACL with OWASP Top 10 rules | WAF attached to API GW prod stage; AWSManagedRulesCommonRuleSet | Amazon API Gateway | Phase 4 | Gap
SEC-A-002 | API Security | Rate Limiting | Max 100 requests/min per IP; burst 200 | API GW Usage Plan + WAF rate-based rule: 100 req/5min window | Amazon API Gateway | Phase 4 | Gap
SEC-A-003 | API Security | API Key Rotation | API keys rotate every 30 days | Secrets Manager rotation Lambda; API GW key auto-update | AWS Secrets Manager | Phase 4 | Gap
SEC-A-004 | API Security | Input Validation | All API inputs validated before Lambda processing | JSON Schema validation in API GW; Lambda request validator enabled on all endpoints | Amazon API Gateway | Phase 1 | Active
SEC-A-005 | API Security | CORS Policy | CORS restricted to approved origins | CORS configured; allow origins restricted to ALB domain | Amazon API Gateway | Phase 1 | Active
AI/LLM Security
SEC-L-001 | AI/LLM Security | Prompt Injection Prevention | Detect and block prompt injection attempts | Bedrock Guardrails: prompt injection filter; input pre-processing Lambda | Amazon Bedrock (Guardrails) | Phase 3 | Gap
SEC-L-002 | AI/LLM Security | Output Filtering (Content Safety) | Filter toxic/harmful content in agent responses | Bedrock Guardrails: content filter (hate, violence, PII) replaces Azure AI Content Safety | Amazon Bedrock (Guardrails) | Phase 2 | Planned
SEC-L-003 | AI/LLM Security | Jailbreak Detection | Block attempts to override system prompt constraints | Bedrock Guardrails: denied topics list; Zero-Inference Cedar policy | Amazon Bedrock (Guardrails), Cedar | Phase 2 | Gap
SEC-L-004 | AI/LLM Security | Approved Models Only | Only Claude models via Bedrock; no Titan, Llama, Mistral | us.anthropic.claude-sonnet-4-6-v1:0 hardcoded default; BEDROCK_MODEL_ID env var in all Lambdas | Amazon Bedrock | Phase 0 | Active
SEC-L-005 | AI/LLM Security | Zero-Inference Policy | Agent must not answer if confidence below threshold | Cedar policy prototype: deny if confidence_score < 0.75 | Cedar (custom prototype) | Phase 2 | Gap
SEC-L-006 | AI/LLM Security | Hallucination Detection | Real-time detection of hallucinated responses | Arize AI Phoenix traces via OpenTelemetry; alert on low grounding score | Arize AI | Phase 3 | Gap
HIPAA
SEC-H-001 | HIPAA | BAA Coverage — Amazon Bedrock | Bedrock must be under Cognizant AWS BAA if processing PHI | Confirm BAA in AWS account 392568849512 covers Bedrock; document | Amazon Bedrock | Phase 3 | Gap
SEC-H-002 | HIPAA | BAA Coverage — S3, DynamoDB, Lambda | Storage and compute must be BAA-covered | Standard AWS services covered under AWS HIPAA BAA; verify account enrollment | Amazon S3, DynamoDB, Lambda | Phase 3 | Gap
SEC-H-003 | HIPAA | PHI in Wiki Pages — Access Control | Wiki pages containing PHI must have access control | Add phi_present flag to frontmatter; Lambda enforces IAM condition on read | Amazon DynamoDB, Amazon S3 | Phase 3 | Gap
SEC-H-004 | HIPAA | Audit Trail for PHI Access | All PHI access must be logged | CloudTrail + DynamoDB audit_log; 7-year retention on audit S3 bucket | AWS CloudTrail, Amazon DynamoDB | Phase 3 | Gap
Supply Chain
SEC-S-001 | Supply Chain | Approved AI Framework Only | No unapproved agentic frameworks (Strands, Kiro) | CI gate: code scan for strands/kiro imports; block merge if found | GitHub Copilot (Actions) | Phase 0 | Planned
SEC-S-002 | Supply Chain | Dependency Scanning | Python packages scanned for CVEs before deploy | Dependabot + pip-audit in GitHub Actions CI pipeline | GitHub Copilot (Actions) | Phase 4 | Planned
SEC-S-003 | Supply Chain | IaC Security Scanning | CDK/CloudFormation scanned before deploy | Checkov scan in CI; block on HIGH severity findings | GitHub Copilot (Actions) | Phase 4 | Planned
6. Skill & Harness Security
SEC-SK-001 | Skill Security | Skill Invocation Traceability | Every skill call must include invoked_by + skill_id for attribution | invoked_by field in all skill payloads; skill_id + latency_ms in all skill responses; stored in wiki-log | AWS Lambda, Amazon DynamoDB | Phase 2 — Complete | Active
SEC-SK-002 | Skill Security | Skill Lambda Error Isolation | Skill failure must not crash calling agent; structured error returned | _PhaseError exception contract; all phase errors return partial phase_results + failed_phase field | AWS Lambda | Phase 2 — Complete | Active
SEC-HRN-001 | Harness Security | Harness State Integrity | Harness run state must be persisted atomically; no lost state on Lambda timeout | DynamoDB UpdateItem after every phase; status=running set at resume start to prevent double-resume | Amazon DynamoDB | Phase 2 — Complete | Active
SEC-HRN-002 | Harness Security | Harness Audit Trail | Every harness run must produce a permanent audit record with full phase results | llmwiki-harness-runs DynamoDB table; phase_results JSONB written after every phase; TTL 30 days (extend for HIPAA) | Amazon DynamoDB | Phase 2 — Complete | Active
SEC-HRN-003 | Harness Security | Human-in-Loop Enforcement | Phase 3 (human input) must be system-enforced; agent cannot bypass | State machine checks human_context == "" and returns status=paused; Lambda will not proceed to Phase 4 without input | AWS Lambda | Phase 2 — Complete | Active
SEC-HRN-004 | Harness Security | Report Data Exposure | Handoff reports must not be publicly accessible; presigned URL only | S3 reports in wiki/reports/ prefix; IAM denies public access; presigned URL 1h TTL (extend to 24h in P3) | Amazon S3 | Phase 3 | Open
SEC-HRN-005 | Harness Security | PHI in Harness Workspace | Engagement context (Phase 3 human input) may contain PHI; must be protected | workspace_files DynamoDB SSE enabled; 30-day TTL; Bedrock Guardrails needed on SK-03 write path (P3) | Amazon DynamoDB, Amazon Bedrock (Guardrails) | Phase 3 | Gap

## AI Governance Standards
Standard ID | Governance Domain | Standard / Policy | Requirement | How LLMWiki Enforces It | Decision Gate | Responsible Party | Status
Model Governance
GOV-M-001 | Model Governance | Approved Models Policy | Only Claude 3.x models via Bedrock; deny Titan, Llama, Mistral, Nova | us.anthropic.claude-sonnet-4-6-v1:0 used in all 9 Lambdas; BEDROCK_MODEL_ID env var; no other models invoked | Phase 0 Go/No-Go | AI Governance Lead | Active
GOV-M-002 | Model Governance | Model Version Pinning | Production agents must pin to a specific Claude model version | Model ARN pinned in CDK; change requires governance board approval | Phase 4 CAB | AI Governance Lead | Planned
GOV-M-003 | Model Governance | Model Change Control | Any model upgrade requires regression test + approval | GitHub PR gate: model ARN change triggers mandatory review + QA sign-off | Phase 4 CAB | ML Engineering Lead | Planned
GOV-M-004 | Model Governance | No Direct Inference Outside KB | Agents must ground answers in LLMWiki KB; no free-form inference | Zero-Inference Cedar policy; Binary Answer Contract in system prompt | Phase 2 Demo | AI Governance Lead | Gap
Agent Governance
GOV-A-001 | Agent Governance | Human-in-Loop for High-Risk Actions | Cutover (UC8), compliance evidence (UC6/UC7) require human approval | Phase 3 of hard harness is system-enforced human gate; SK-03 human_review_required=true for high-risk pages | Phase 3 UAT | Product Owner | Active
GOV-A-002 | Agent Governance | Agent Identity Registration | Every AgentCore agent must have a registered identity | agent_id passed in all skill invocations; uc1-harness, uc1-orchestrator-v1 identities registered | Phase 2 Demo | DevOps Lead | Active
GOV-A-003 | Agent Governance | Agent Contribution Limits | Agents cannot publish wiki pages directly without review | SK-03 WikiContributeSkill writes to pending/ staging; human_review_required flag; Streamlit review queue | Phase 1 Demo | ML Engineering Lead | Active
GOV-A-004 | Agent Governance | Agent-to-Agent (A2A) Protocol | A2A communication must use approved protocol; validate for Neuro AI | AgentCore native A2A; validate compatibility with Neuro AI roadmap | Phase 3 Review | Enterprise Architect | Planned
Knowledge Governance
GOV-K-001 | Knowledge Governance | contributing_agent Frontmatter | All wiki pages must declare source and contributing agent | SK-03 contribution frontmatter: contributing_agent, agent_id, use_case, skill_id on all wiki writes | Phase 1 Demo | ML Engineering Lead | Active
GOV-K-002 | Knowledge Governance | human_review_required Flag | High-risk or agent-authored pages require SME review before publish | human_review_required flag set on all SK-03 contributions; Phase 3 is system-enforced pause gate | Phase 1 Demo | ML Engineering Lead | Active
GOV-K-003 | Knowledge Governance | Pending/ Staging Area | Agent-contributed pages held in pending/ until approved | DynamoDB status: pending → under_review → approved → published flow implemented in SK-03 | Phase 1 Demo | ML Engineering Lead | Active
GOV-K-004 | Knowledge Governance | Content Expiry Policy | Wiki pages older than 12 months must be reviewed for accuracy | TTL-like flag: last_reviewed_at + EventBridge rule to flag stale pages | Phase 3 Review | Content Owner | Planned
GOV-K-005 | Knowledge Governance | Domain Tagging Required | All pages must be tagged with ≥1 use_case domain tag | use_case tag required in all skill invocation payloads; Lambda validates presence | Phase 1 Demo | ML Engineering Lead | Active
Vector Alignment Governance
GOV-V-001 | Vector Alignment | V1/V2/V3 Alignment Tagging | All wiki content tagged with alignment tier per AI Handbook | alignment_tier field in frontmatter; V1=foundational, V2=operational, V3=strategic | Phase 3 Review | AI Governance Lead | Planned
GOV-V-002 | Vector Alignment | Quarterly Alignment Report | Report on % of content at each alignment tier; coverage per UC | Streamlit dashboard: alignment tier distribution; export to Microsoft Fabric | Phase 3 Review | AI Governance Lead | Planned
GOV-V-003 | Vector Alignment | No V3 Content in POC | Strategic (V3) content not exposed to agents until governance approved | IAM condition on /wiki/ask: deny alignment_tier=V3 in Phase 0–2 | Phase 2 Demo | AI Governance Lead | Planned
Data Lineage
GOV-L-001 | Data Lineage | Source Traceability | Every agent answer must be traceable to a source document | Lambda stores lineage chain: source_doc_id → wiki_page_id → query_id → answer_id | Phase 3 UAT | ML Engineering Lead | Gap
GOV-L-002 | Data Lineage | Citation in Agent Responses | Agent must return source citations in every answer | Binary Answer Contract: sources[] field required; empty sources = invalid response | Phase 2 Demo | ML Engineering Lead | Planned
GOV-L-003 | Data Lineage | Lineage Visualization | SMEs can trace any response back to source document | Streamlit lineage view: click answer → see wiki page → see source doc | Phase 3 Review | FE Dev Lead | Planned
Hallucination Controls
GOV-H-001 | Hallucination Controls | Zero-Inference Policy | Agent must respond 'unknown' if no grounded answer available | Cedar policy prototype: deny if confidence_score < 0.75; return structured unknown | Phase 2 Demo | AI Governance Lead | Gap
GOV-H-002 | Hallucination Controls | Binary Answer Contract | Agent responses must be yes/no/unknown with evidence | Binary Answer Contract enforced in SK-02 system prompt + Lambda response schema validation | Phase 2 Demo | ML Engineering Lead | Active
GOV-H-003 | Hallucination Controls | Confidence Scoring | All /wiki/ask responses include confidence score | SK-02 returns confidence: high/medium/low; Phase 6 gap detection triggered on non-high confidence | Phase 2 Demo | ML Engineering Lead | Active
Bias & Fairness
GOV-B-001 | Bias & Fairness | Multi-UC Test Coverage | Knowledge base must serve all 10 UCs equitably; no single-UC bias | Seed content targets ≥20 pages per UC; recall tested per UC in Phase 3 | Phase 3 UAT | QA Lead | Planned
GOV-B-002 | Bias & Fairness | No Demographic Bias in Runbooks | Runbooks/playbooks must not encode role-based bias | Content review checklist; Bedrock Guardrails PII/bias filter enabled | Phase 3 Review | Content Owner | Planned
Audit & Compliance
GOV-C-001 | Audit & Compliance | CloudTrail for All API Calls | All API Gateway and Lambda invocations logged in CloudTrail | CloudTrail trail active; all API Gateway + Lambda invocations logged; S3 retention configured | Phase 0 Go/No-Go | SecOps Lead | Active
GOV-C-002 | Audit & Compliance | DynamoDB Contribution Audit Log | Every wiki contribution recorded with agent, timestamp, action | wiki_audit DynamoDB table; append-only; PITR enabled | Phase 3 UAT | ML Engineering Lead | Gap
GOV-C-003 | Audit & Compliance | Monthly Governance Report | Monthly report: contributions, reviews, approvals, model usage | Athena query over audit logs; export to Microsoft Fabric dashboard | Phase 3 Review | AI Governance Lead | Planned
GOV-C-004 | Audit & Compliance | HIPAA Audit Trail | PHI access logged separately with 7-year retention | DynamoDB audit_log TTL=never for PHI rows; dedicated S3 bucket | Phase 3 UAT | SecOps Lead | Gap
Skill & Harness Governance
GOV-SK-001 | Skill Governance | Skill Registry as Source of Truth | All deployed skills must be registered in the skill manifest with skill_id, version, owner | Skill manifest in LLMWikiDesign.md §20.2; SSM parameters for ARN discovery; Terraform outputs for ARN references | Phase 2 Review | ML Engineering Lead | Active
GOV-SK-002 | Skill Governance | Skill Versioning Policy | Breaking skill contract changes require version bump and backward-compat period | Skill contract: {inputs, invoked_by} → {skill_id, business_name, status, outputs, latency_ms}; change requires SK-XX v2 new Lambda | Phase 3 CAB | ML Engineering Lead | Planned
GOV-SK-003 | Skill Governance | Skill Business Name Attribution | All skill responses carry business_name for stakeholder-facing display | business_name field in all skill responses (e.g. "Delivery Risk & Gap Analysis"); displayed in Streamlit skill badges | Phase 2 Review | Product Owner | Active
GOV-HRN-001 | Harness Governance | Phase State Machine as Governance Record | Hard harness phases enforce due-diligence gates; phase completion = governance checkpoint | 8-phase UC1 hard harness maps to engagement lifecycle gates: classify → human input → risk → gaps → template → handoff | Phase 2 Demo | AI Governance Lead | Active
GOV-HRN-002 | Harness Governance | Phase 3 Human Gate is Non-Bypassable | System must not allow risk analysis (Phase 5) without confirmed human context input | uc1_harness Lambda returns status=paused if human_context empty; UI requires explicit user input; enforced in code not prompt | Phase 2 Demo | AI Governance Lead | Active
GOV-HRN-003 | Harness Governance | Gap Severity Classification | Harness must classify detected gaps as blocking or non-blocking | Phase 6 produces blocking: true/false per gap; blocking_count surfaced in Phase 8 report and Streamlit telemetry | Phase 2 Demo | Product Owner | Active
GOV-HRN-004 | Harness Governance | Harness Completion = Auditable Deliverable | Every completed harness run must produce an S3 report + indexed wiki page as auditable output | Phase 8 writes wiki/customers/{id}-harness-handoff-{year}.md to S3 via SK-03 + plain-text report to wiki/reports/ | Phase 3 UAT | SecOps Lead | Active
GOV-HRN-005 | Harness Governance | Partial Phase Results on Failure | If harness errors mid-run, completed phase outputs must be preserved and recoverable | _PhaseError contract returns phase_results up to failed_phase; DynamoDB status=error with partial results; UI shows per-phase success/failure | Phase 3 UAT | ML Engineering Lead | Active

## POC Checklist — UC1 S2S
Check ID | Layer | Test Item | Success Criterion | Tool / Service | Priority | Status | Notes
LLMWiki Infrastructure Checks
CHK-L-001 | LLMWiki | LLMWiki deployed and accessible | API GW endpoint returns HTTP 200 on GET /health; no auth error | Amazon API Gateway, AWS Lambda | P1 | Pass | ALB endpoint http://llmwiki-alb-1382316210.us-east-1.elb.amazonaws.com/ returns 200
CHK-L-002 | LLMWiki | S3 bucket created with SSE-S3 | S3 console shows Server-side encryption: SSE-S3 on llmwiki-kb-prod | Amazon S3 | P1 | Pass | SSE-S3 on llmwiki-278e7e22; verified via aws s3api get-bucket-encryption
CHK-L-003 | LLMWiki | DynamoDB tables created (wiki_pages, contributions, audit_log) | All 3 tables visible in DynamoDB console; PITR enabled | Amazon DynamoDB | P1 | Pass | 7 DynamoDB tables deployed including harness_runs + workspace_files; all with SSE
CHK-L-004 | LLMWiki | Bedrock Knowledge Base created and synced | KB status = ACTIVE; sync job = COMPLETE; >0 documents indexed | Amazon Bedrock Knowledge Base | P1 | Pass | Bedrock KB ACTIVE; S3 Vectors data source; claude-sonnet-4-6 model
CHK-L-005 | LLMWiki | Seed content ingested (≥20 pages) | /wiki/ask returns non-empty sources[] for 5 known-good queries | Amazon Bedrock, Amazon S3 | P1 | Pass | Seed content ingested; /wiki/ask returns sources[] for known queries
CHK-L-006 | LLMWiki | Streamlit UI accessible | UI loads at http(s)://<host>:8501; can browse wiki pages | Streamlit on EC2/Fargate | P2 | Pass | Streamlit accessible at ALB URL; 4 pages: skills_hub, skill_builder, agent_demo, harness_demo
CHK-L-007 | LLMWiki | Human review queue visible in Streamlit | Pending pages appear in review queue; SME can approve/reject | Streamlit, Amazon DynamoDB | P2 | Not Started | Test with a manually submitted pending page
Business Knowledge API Checks
CHK-A-001 | Business Knowledge API | /wiki/ask returns structured JSON | POST /wiki/ask with test query returns {answer, sources[], confidence, query_id} | Amazon API Gateway, AWS Lambda, Amazon Bedrock | P1 | Pass | /wiki/ask returns {answer, sources[], confidence, query_id}
CHK-A-002 | Business Knowledge API | /wiki/ask confidence score present | Response JSON includes confidence field; value between 0.0 and 1.0 | Amazon Bedrock KB, AWS Lambda | P1 | Pass | confidence field present; low confidence triggers SK-05 gap detection
CHK-A-003 | Business Knowledge API | Binary Answer Contract enforced | Query with yes/no question returns answer='yes' or 'no' or 'unknown'; never free-form | Claude 3.5 Sonnet, AWS Lambda | P1 | Not Started | Test: 'Is customer X provisioned in us-east-1?'
CHK-A-004 | Business Knowledge API | /wiki/contribute creates pending page | POST /wiki/contribute returns 201; DynamoDB shows new pending page with human_review_required=true | Amazon API Gateway, AWS Lambda, Amazon DynamoDB | P1 | Pass | /wiki/contribute creates pending page; human_review_required=true; contributing_agent in frontmatter
CHK-A-005 | Business Knowledge API | UC1 playbook endpoint works | POST /wiki/ask?domain=UC1 returns UC1-specific sources only | Amazon Bedrock (domain filter), AWS Lambda | P1 | Pass | UC1 playbook endpoint works; domain filter applied in Bedrock query
AgentCore Integration Checks
CHK-C-001 | AgentCore | MCP tool wiki_ask registered in AgentCore | Tool appears in AgentCore tool registry; schema validates | Amazon Bedrock (AgentCore) | P1 | Pass | wiki_ask MCP tool registered; schema validated
CHK-C-002 | AgentCore | MCP tool wiki_contribute registered | wiki_contribute tool appears; POST schema includes title, content, contributing_agent | Amazon Bedrock (AgentCore) | P1 | Pass | wiki_contribute MCP tool registered; POST schema matches /wiki/contribute spec
CHK-C-003 | AgentCore | AgentCore Gateway IAM role configured | AgentCore can invoke Lambda via SigV4; no auth errors in CloudWatch | Amazon Bedrock (AgentCore), AWS IAM | P1 | Pass | AgentCore IAM role deployed; SigV4 enforced; no auth errors in CloudWatch
CHK-C-004 | AgentCore | UC1 Sales-to-Service agent deployed | Agent status = ACTIVE in AgentCore console; model = Claude 3.5 Sonnet | Amazon Bedrock (AgentCore) | P1 | Pass | llmwiki-uc1-orchestrator Lambda deployed; Claude Sonnet 4.6; all 5 skills wired
CHK-C-005 | AgentCore | Agent invokes wiki_ask tool successfully | UC1 agent query triggers wiki_ask tool call visible in CloudWatch trace | Amazon Bedrock (AgentCore), AWS CloudWatch | P1 | Pass | UC1 orchestrator invokes SK-02 wiki_ask; visible in CloudWatch logs
CHK-C-006 | AgentCore | Agent identity stored in wiki contribution | DynamoDB contribution record shows agent_id from AgentCore context | Amazon DynamoDB, Amazon Bedrock (AgentCore) | P1 | Pass | agent_id=uc1-harness recorded in wiki-log DynamoDB on every SK-03 contribution
TAG→AgentCore Migration Checks (from Matrix)
CHK-T-001 | TAG→AgentCore | Persona manifest migrated to AgentCore config | UC1 agent has equivalent persona config; no missing TAG fields | Amazon Bedrock (AgentCore) | P1 | Not Started | Document any fields that cannot be migrated as G-016 gap
CHK-T-002 | TAG→AgentCore | Zero-Inference Policy (Cedar prototype) deployed | Lambda authorizer denies /wiki/ask response if confidence < 0.75 | Cedar prototype, AWS Lambda | P1 | Not Started | Test with deliberately low-confidence query
CHK-T-003 | TAG→AgentCore | Binary Answer Contract validated in AgentCore | Malformed response (no answer field) rejected by Lambda validator | AWS Lambda, Claude (Anthropic) | P1 | Not Started | Test with adversarial prompt that bypasses contract
CHK-T-004 | TAG→AgentCore | Bedrock Guardrails replace Azure AI Content Safety | Guardrails configured: prompt injection, PII, denied topics; Azure safety not called | Amazon Bedrock (Guardrails) | P1 | Pass | Bedrock Guardrails configured; no Azure endpoint calls in CloudWatch
CHK-T-005 | TAG→AgentCore | No-fallback routing: no answer if KB miss | Agent returns answer='unknown' (not a hallucinated answer) on KB miss | Cedar, AWS Lambda, Amazon Bedrock | P1 | Not Started | Test with a question that has zero KB matches
CHK-T-006 | TAG→AgentCore | Azure AI Search bridge Lambda working | Queries to legacy Azure AI Search proxied correctly via Lambda | AWS Lambda (bridge) | P2 | Not Started | Required until full KB migration; verify fallback latency < 5s
CHK-T-007 | TAG→AgentCore | Agent-to-Agent (A2A) protocol tested | UC1 agent can invoke another AgentCore agent (e.g. UC2) via A2A | Amazon Bedrock (AgentCore) | P2 | Not Started | Validate for Neuro AI roadmap compatibility
CHK-T-008 | TAG→AgentCore | HIPAA BAA components confirmed | Checklist of covered services submitted to SecOps | Amazon Bedrock, S3, DynamoDB, Lambda, API GW | P1 | Not Started | See G-021; must complete before any PHI data ingested
CHK-T-009 | TAG→AgentCore | Arize AI hallucination tracing active | OpenTelemetry traces visible in Arize Phoenix dashboard; no gaps | Arize AI | P2 | Not Started | Phase 3 requirement; note as P2 for POC baseline
End-to-End Flow Checks
CHK-E-001 | End-to-End | SOW upload → wiki page flow | Upload SOW PDF → Textract → markdown → S3 → KB sync → queryable in <5 min | Amazon Textract, S3, Bedrock KB | P1 | Not Started | Use a real UC1 SOW (sanitized); measure end-to-end latency
CHK-E-002 | End-to-End | Agent query → structured response | UC1 agent query returns structured JSON with answer + evidence + confidence | Amazon Bedrock (AgentCore), LLMWiki API | P1 | Pass | 20 UC1 queries via UC1 Orchestrator; all 5 skills executed; phase results captured
CHK-E-003 | End-to-End | Agent contribution → human review → published | Agent POSTs wiki page → SME approves in Streamlit → page promoted to KB | LLMWiki full stack | P1 | Not Started | Measure approval latency; verify KB re-sync triggered
CHK-E-004 | End-to-End | CloudTrail logs all API calls | Every /wiki/ask and /wiki/contribute call visible in CloudTrail S3 bucket | AWS CloudTrail | P1 | Pass | CloudTrail active; all /wiki/ask and /wiki/contribute calls visible in trail
CHK-E-005 | End-to-End | POC demo: 15-minute walkthrough passes | Stakeholder demo: ingest → query → contribute → review flow completes without error | Full stack | P1 | Not Started | Record Loom; distribute before Phase 2 sign-off
Skill Architecture Checks (Phase 2 — Complete)
CHK-SK-001 | Skill Architecture | All 5 POC skills deployed and accessible | aws lambda list-functions returns llmwiki-skill-{context-bootstrap,wiki-query,wiki-contribute,artifact-resolution,gap-detection} | AWS Lambda | P1 | Pass | All 5 ARNs confirmed in account 392568849512 us-east-1
CHK-SK-002 | Skill Architecture | SK-01 ContextBootstrapSkill smoke test | Invoke with {inputs:{customer_id:"test"}} returns {skill_id:"SK-01", outputs:{customer_status, pages_found}} | AWS Lambda | P1 | Pass | Tested with CUST001; customer_status=no-history; pages_found=0
CHK-SK-003 | Skill Architecture | SK-02 WikiQuerySkill smoke test | Returns {confidence: high¦medium¦low, answer, action_items[], wiki_pages_used} | AWS Lambda, Amazon Bedrock KB | P1 | Pass | confidence=medium for QNXT risk query; action_items populated
CHK-SK-004 | Skill Architecture | SK-03 WikiContributeSkill smoke test | Creates wiki page; DynamoDB log entry with contributing_agent; human_review_required in response | AWS Lambda, Amazon DynamoDB | P1 | Pass | Page indexed to wiki/customers/; agent_id=uc1-harness logged
CHK-SK-005 | Skill Architecture | SK-04 ArtifactResolutionSkill smoke test | Returns {found, completion_pct, populated_fields[], missing_fields[]} for persona-template | AWS Lambda | P1 | Pass | found=false for new customer; completion_pct=0; missing_fields listed
CHK-SK-006 | Skill Architecture | SK-05 GapDetectionSkill smoke test | Returns {gaps:[{gap_type, title, blocking, human_prompt, gap_id}]} for low-confidence context | AWS Lambda | P1 | Pass | 5-8 gaps returned per invocation; blocking gaps correctly classified
CHK-SK-007 | Skill Architecture | UC1 Orchestrator invokes all 5 skills sequentially | CloudWatch logs show SK-01 → SK-02 → SK-03 → SK-04 → SK-05 invocations in order | AWS Lambda, Amazon CloudWatch | P1 | Pass | Full execution trace visible; total latency ~60s for full 6-step run
CHK-SK-008 | Skill Architecture | Skills Hub Streamlit page accessible | /skills_hub loads; 5 skill cards with Live Demo and invoke buttons | Streamlit, ALB | P2 | Pass | http://llmwiki-alb-1382316210.us-east-1.elb.amazonaws.com/skills_hub
CHK-SK-009 | Skill Architecture | Agent Demo step-by-step mode works | /agent_demo 6-step mode: SK-01…SK-05 execute with skill badges + latency display | Streamlit, ALB | P2 | Pass | All steps verified; graceful degradation if Lambda not deployed
CHK-SK-010 | Skill Architecture | Skill not deployed → friendly error (no crash) | check_not_deployed() shows deploy command banner instead of ResourceNotFoundException | Streamlit | P2 | Pass | Wrapped in try/except; warning banner with terraform apply command shown
Hard Harness Checks (Phase 2 — Complete)
CHK-HRN-001 | Hard Harness | harness_runs DynamoDB table deployed | aws dynamodb describe-table --table-name llmwiki-harness-runs returns ACTIVE | Amazon DynamoDB | P1 | Pass | PAY_PER_REQUEST; 2 GSIs; SSE enabled; TTL on expires_at
CHK-HRN-002 | Hard Harness | workspace_files DynamoDB table deployed | aws dynamodb describe-table --table-name llmwiki-workspace-files returns ACTIVE | Amazon DynamoDB | P1 | Pass | PAY_PER_REQUEST; phase_index GSI; SSE enabled; TTL on expires_at
CHK-HRN-003 | Hard Harness | Gatekeeper Lambda smoke test | Invoke llmwiki-gatekeeper with {customer_id:"TEST"} returns {ready:true, message, phases[8]} | AWS Lambda | P1 | Pass | Returns Claude-generated greeting + full 8-phase manifest; tested with CUST001
CHK-HRN-004 | Hard Harness | Harness Phase 1-2 run and pause at Phase 3 | Invoke llmwiki-uc1-harness with human_context="" returns {status:paused, question, current_phase:3} | AWS Lambda, Amazon DynamoDB | P1 | Pass | Ran in ~10s; 3 contextual questions generated based on Phase 2 classification
CHK-HRN-005 | Hard Harness | Harness resume: all 8 phases complete | Resume invoke with human_context filled returns {status:completed, phases_completed:8, report_download_url} | AWS Lambda, Amazon Bedrock, Amazon S3 | P1 | Pass | BCBS-MN run: 8 phases in ~60s; 9 gaps; S3 report generated; presigned URL valid
CHK-HRN-006 | Hard Harness | get_status polling action works | Invoke with {action:get_status, engagement_id} returns {status, phases_done, phase_results} in <200ms | AWS Lambda, Amazon DynamoDB | P1 | Pass | DynamoDB read ~100ms; returns partial phase_results during run; full results on completion
CHK-HRN-007 | Hard Harness | Async invoke + polling UI works end-to-end | After Phase 3 input, UI fires Event invoke; phase tiles animate live every 3s; completion message appears | Streamlit, AWS Lambda, Amazon DynamoDB | P1 | Pass | No blocking spinner; user sees progress within 3s of submitting Phase 3 answer
CHK-HRN-008 | Hard Harness | harness_demo.py page accessible at /harness_demo | /harness_demo returns HTTP 200; two-column layout loads; gatekeeper Start button visible | Streamlit, ALB | P1 | Pass | http://llmwiki-alb-1382316210.us-east-1.elb.amazonaws.com/harness_demo
CHK-HRN-009 | Hard Harness | S3 handoff report generated and downloadable | Phase 8 writes wiki/reports/{id}-handoff-report-{date}.txt; presigned URL returned; download works | Amazon S3, AWS Lambda | P1 | Pass | BCBS-MN report: wiki/reports/bcbs-mn-001-handoff-report-2026-05-15.txt; download verified
CHK-HRN-010 | Hard Harness | Wiki handoff page indexed via SK-03 | Phase 8 SK-03 contribution creates wiki/customers/{id}-harness-handoff-{year}.md in S3 + DynamoDB | Amazon S3, Amazon DynamoDB | P1 | Pass | wiki/customers/bcbs-mn-001-harness-handoff-2026.md verified in S3
CHK-HRN-011 | Hard Harness | Phase 3 hint visible to user | After Phase 2, chat panel shows question text + info box with example answer | Streamlit | P2 | Pass | Blue info box with example: "No prior attempts. CMO is exec sponsor. HIPAA required..."
CHK-HRN-012 | Hard Harness | Telemetry sidebar updates live during polling | Sidebar shows phases done, skills used, gaps logged, total ms — updates every 3s during run | Streamlit, Amazon DynamoDB | P2 | Pass | Metrics cast to int() to avoid ValueError on DynamoDB string numbers
CHK-HRN-013 | Hard Harness | Reset Harness clears all session state | Reset button clears harness_result, polling state, chat_messages; fresh gatekeeper start | Streamlit | P2 | Pass | All 8 session keys cleared: harness_result, gatekeeper_done, harness_running, phase3_question, phase3_answered, chat_messages, harness_polling, harness_run_id, harness_phase3_ctx
CHK-HRN-014 | Hard Harness | IAM: Streamlit can invoke gatekeeper + uc1_harness | ECS task role allows lambda:InvokeFunction on llmwiki-gatekeeper and llmwiki-uc1-harness ARNs | AWS IAM, AWS Lambda | P1 | Pass | llmwiki-streamlit-skills-invoke policy updated; verified via CloudWatch — no auth errors
CHK-HRN-015 | Hard Harness (P3) | Cognito/SSO auth on Streamlit UI | ALB listener requires authentication before serving harness_demo page | Amazon Cognito, ALB | P1 | Not Started | Required before any real customer engagement data processed
CHK-HRN-016 | Hard Harness (P3) | DOCX output from harness Phase 8 | Phase 8 produces formatted .docx file downloadable from Streamlit | AWS Lambda (container), python-docx | P2 | Not Started | Current output is plain-text .txt; python-docx layer needed